## Sheet1
Test Plan Schedule | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
TASK 1 | Week 1: Unit Testing
TASK 2 | Week 3: Performance and Stress Testing
TASK 3 | Week 4: System Integration
TASK 4 | Week 5: User Acceptance
TASK 5 | Week 8: Automated Regression Test | Estimated Delivery:
TASK 6 | Week 10: Beta testing | 12 Weeks
Resources Roles/Responsibility
Deliverable | Week 1: Role; Week 2: Responsibility
Ryan/Conor | Week 1: Unit testing; Week 3: Create test cases for unit testing
Robert/Liam | Week 1: Integration Testing; Week 3: Create a test case for the integration testing of the entire system
Conor/Robert | Week 1: Performance Testing; Week 3: Performance and stress testing of the game continuously until achieving a fail result.
Liam/Ryan | Week 1: Acceptance Testing; Week 3: Confirming the system is ready for release.
Conor | Week 1: install tester; Week 3: Making sure the game can be installed onto all listed devices.
Robert | Week 1: Automated Tester; Week 3: This is the proces of re running previously completed test to insure no functionality has changed.
John | Week 1: Bug Fixes; Week 3: Fixing any and all glitches/bugs in the game
Conor | Week 1: Project Manager; Week 3: Oversees the entire testing process.
Risk | Week 1: Probability; Week 2: Mitigation Plan
Data Corrupion/Loss | Week 1: High; Week 2: The team must insure they backup files frequently to avoid any loss of data or progress.
Files are stored on multiple servers.
Schedule Backlog | Week 1: Med; Week 2: The team must follow a stict documenting process so progress can be tracked.
Management assigned an extra staff member to assist all project teams.
System Crash | Week 1: Med; Week 2: A number of backups are made
Backup machines are left nearby which can be accessed should the system crash
Staff Absence | Week 1: Low; Week 2: extra staff have been assigned to the test case to account for possible absences.
Insufficent Testers | Week 1: Low; Week 2: Project leaders can easily fill this spot or re allocate staff to new roles.